Given the information provided below and the Gantt chart structure, you are to construct a Gantt chart

|  |  |  |  |
| --- | --- | --- | --- |
| Activity Letter | **Activity Description** | Predecessor | **Duration (months)** |
| A | Train project team | None | 1 |
| B | Project paperwork and systems design | A | 2 ½ |
| C | Modify purchased package | B | 2 |
| D | Manual systems flow | B | 1 ½ |
| E | Modify in-house procedures | B | 4 |
| F | Test and implement modifications to purchased package | C | 1 ½ |
| G | Test and implement manual | D | ¾ |
| H | Test and implement modifications to in-house procedures | E | 1 |